## Group_18May
Board: Motherboard
Revision: REV20200407C
Designer: Ashad Farhan
Reviews | Implemented | Designer comment
Add 3.3V pour to bottom and 5V to layer 3 | Yes
Long SPI connection, check if its fine, propogation delay | Checked | The shew is 6.5% in the longest trace.
Mounting hole spacing, check hammond cabinet | Added | The horizontal seperation of most of the mounting holes match with the pitch of this -> | Hommond mounting rack
Square first pin marker for throu hole | Added
Required one extra mounting hole near the right side (close to connectors) | No | Because of lack of space, moved existing center mounting hole to the right

## Nathan_1
Board: Motherboard
Revision: REV20200407C
Designer: Ashad Farhan
Reviews | Implemented | Designer comment
I would make the stitching vias tented so they are more hidden (set the tented checkbox for both top and bottom solder masks) | No | GND plane in bottom removed. I have tented all other vias | Please let me know if this fine
As a user, not obvious what "S" and "D" mean for the jumpers. Lots of space for silkscreen labels, perhaps add instructions to that center part of the PCB. Also, perhaps add silkscreen arrow which points at the DCs that are to be used in series etc. | Yes
PCB label "Sensor Motherboard REV123123" can't be seen. This is because you have it on the top copper layer (which is fine), but the soldermask covers it. If you want the label to be in copper, you need to cut out the soldermask above the text. See older AMDC revisions for examples of this (just copy text from copper layer to soldermask layer). Or, just put the label in silkscreen. | Yes | Silkscreen is used
Not sure how I feel about the very split GND layer (layer 2)... I can see you basically merged GND pour onto bottom layer.. this is okay i suppose, but HF return currents for SPI signals running horizontally across the middle of the PCB on layer 3 will have have issues, since there isn't a continuous return path across the middle of the board... Perhaps now that routing is "done", stare at it and think about consolidating the power rails to less layers so that layer 2 and be more continuous | Yes
Label the DB-15 connectors with silkscreen layer.. Which one is GPIO vs AMDC connection?? ==> whoops, just saw it says "AMDC Link" ...maybe make that larger font? and still add the GPIO label | Yes
Don't really like the little resistors/caps between the DC/DCs.. How on earth are you supposed to rework those if needed? | Yes
LED3..6 routing needs work... looks like tracks got shifted around..? | Yes
C41 is going to hit the MCU, see 3D view. | Yes
In general: you tend to put vias RIGHT next to pads... Think about the soldering process... the solder paste will go into the via if the copper is continuous with no soldermask... See C18. its nearly via-in-pad! I wouldn't do this. | Yes
Don't forget, you can run traces under the MCU on the top layer if needed | ok
I wouldn't change it now, but the DB-15 connectors are half-way off the PCB.. This will probably work, but strain relief on the cable is not good.. if cable flexes up and down, this flexes the PCB. If the whole DB-15 connector was on the PCB, it would be more stable | No | will keep in mind next time
T1 extends significantly beyond the silkscreen (see 3D view)... Therefore, you can't see label T1 when populated, and R14 / U5 are pretty close to it… | Yes