## Nathan_1
Board: Motherboard
Revision: REV20200407C
Designer: Ashad Farhan
Reviews | Implemented | Designer comment
The title block doesn't have the "ProjectGroup" etc box filled in, add this to match the AMDC schematics. You have to edit the project options to add these parameters. | Yes
Fix BOM. BOM is a pain, but a good BOM saves SO MANY HEADACHES. You should add the required parameters to each component in the schematic such that the BOM tool outputs a file you can directly upload to Digi-Key (i.e. ensure Supplier 1 and Supplier Part Number 1 parameters are set; it looks like 2/3 of the components have this set. If you set these, Altium can go fetch device info from the server!) When you generate the BOM, group columns by Supplier Part Number 1 and you should rows for each thing to order from digi-key. Make sure BOM is right, otherwise it will waste a lot of time during fab (I learned this the hard way). Double check, triple check the BOM. Try uploading the resulting CSV BOM file up to Digi-Key to create a cart. Does it work? Are there parts out of stock? Spend a few hours getting the BOM in tip-top shape :slightly_smiling_face: | Yes
Fix value label locations (e.g. C3) => easy way to do this is just rotate component a few times, as Altium will usually auto-place the value label (select component and hit SPACE a few times) | Yes
Reason for MCU PD8..10 being labeled out of order? I presume due to routing, but would be nice if they mapped 1:1 to the connector pins... Makes it easy on user: "ah, pin 1 goes to PD0, pin 10 goes to PD9, etc) | Yes
^^ following previous comment, can you swap CON4A pins to make I/O pins be contiguous? i.e. no GND on pin 11. Unless there is a good reason for this GND | Yes
For MCU power, we don't need the 10n caps.. just adds another item to the BOM. You only have two 10n caps on the board, C31 and C29. Since we aren't using the analog part of the MCU, I would just use 100n caps as you use elsewhere. | Yes
Set component Type field in the schematic to the correct thing. This affects BOM output. For example, all the daughtercards in the schematic (i.e. DC1..8) should not be "Standard". I believe use "Standard (No BOM)" so they don't appear on BOM to upload to digi-key, etc. Another one: the title block should be "Graphical" so it doesn't appear on the BOM LED5, LED6 direction polarity is wrong | Yes
The whole board has a single 11k resistor ... you can probably use a 10k resistor and be fine, as this just sets trim for the 5V DC/DC. Consider these types of BOM optimizations. (if you need 11k, consider using combinations of the other popular resistors you already have in the BOM, maybe 10k + 1.2k) | Yes | 10k is used here